## Sheet1
Id | Start time | Completion time | Email | Name | PU | Sub PU | Date | Shift | Rank | Machine Name | Engine/Component Loss | Break down phenomena | WHY 1 | WHY 2 | WHY 3 | WHY 4 | WHY 5 | Root cause | ICA | PCA | Responsibilty | Status | Target Date | Breakdown Type | Classification | Breakdown time (in mins) | Spare Replaced | Spare Details If Replaced
1 | 2024-11-22 08:46 | 2024-11-22 08:50 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-11-21 | 1 | B | Marposs | 4 | Main conveyor trip | part stuck. load on conveyor. | . | . | . | . | part stuck | 2 | 2 | kunal | Open | 2024-11-27 | M | Basic Condition | 15 | No | 2
2 | 2024-11-22 15:15 | 2024-11-22 15:20 | 23112700@mahindra.com | SANTOSH CHAUDHARI | Machine Shop | Block line 1 | 2024-11-22 | 1 | B | Gehring | 75 | stroke unclamp pr. sw fault for spindle 1 | air pressure confirmation missed | set pressure not reached | air leakages from the pipe | pipe punctured | Improper routing | Improper routing | Damaged pipe cut and rejoin remaining pipe with straight conenctor | 1. PU pipe routing corrected. 2. All pipe checked for other machines. | Umakant ,Santosh | Closed | 2024-11-29 | M | Basic Condition | 120 | Yes | pu 6 straight connector-1 nos
3 | 2024-11-22 23:00 | 2024-11-22 23:05 | 23147252@mahindra.com | SHAIK SABIR | Machine Shop | Block line 1 | 2024-11-22 | 1 | A | Final Washing | 5 | Washing pressure low | washing pressure not reached as per specification | Internal leakage from other turret | Turret o-ring damage | life over |  | Turrent O-ring life over | Turrent RPM increased from 450 to 480 rpm | All o ring replaced | sabir.Sandeep | Closed | 2024-11-24 | M | Deterioration | 10 | Yes | O ring required
4 | 2024-11-22 23:56 | 2024-11-23 00:10 | 25024032@mahindra.com | SANDIP PATHE | Machine Shop | Block line 1 | 2024-11-22 | 2 | A | Gehring | 40 | Pressure switch fault | back press not develop | Air leakage from PU pipes and fittings | Pipe brust and pu fitting damaged | Fitting stuck and pipe pinched in moving parts | pipe routine is not proper | pipe routine not prper | temporarily pipe replaced | need to replace all pu pipes and required proper routine | Sandip/Umakant | Closed | 2024-12-02 | M | Poor Skill | 90 | No
5 | 2024-11-26 00:23 | 2024-11-26 00:26 | 25025247@mahindra.com | RAMCHANDRA LATKE | Machine Shop | Block line 1 | 2024-11-25 | 2 |  | Gehring | 5 | Pregaugeing station locating pin advance return issue | [5 empty] | Sensor position disturb | Sensor setting done working ok |  |  | Closed
6 | 2024-11-28 14:59 | 2024-11-28 15:03 | 25025247@mahindra.com | RAMCHANDRA LATKE | Machine Shop | Block line 1 | 2024-11-28 | 3 |  | Heller 815/ Heller 810 | 7 | Chip conveyour level exceed | [6 empty] | Cleaned filter & level sensors unit
7 | 2024-11-29 08:44 | 2024-11-29 08:53 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-11-28 | 2 |  | Gehring | 22 | stroke unclamp pr. sw fault for spindle 1 | air pressure confirmation missed | set pressure not reached | air leakages from the pipe | pipe punctured | Improper routing | Improper routing | Damaged pipe cut and rejoin remaining pipe with straight conenctor | 1. PU pipe routing corrected. 2. All pipe checked for other machines. | Umakant ,Santosh | Closed | 2024-11-29 | M | Basic Condition | 120 | Yes | pu 6 straight connector-1 nos
8 | 2024-11-29 08:53 | 2024-11-29 08:57 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-11-28 | 2 |  | Final Washing | 10 | washing pressure high and low, bag filters clogged | [5 empty] | leakages and blockage at turrets | recovered and started | valve replacement to be planned on sunday. | sandip, sabir, santosh, umakant | Open | 2024-12-01 | M | Deterioration | 25 | No
9 | 2024-11-30 00:22 | 2024-11-30 00:26 | 25027844@mahindra.com | SACHIN PATIL | Machine Shop | Block line 1 | 2024-11-29 | 2 |  | Final Washing | 10 | Washing Pressure low | [5 empty] | Pressure adjusted by RPM Set | RPM Set |  |  | Closed |  | E and M |  |  | No
10 | 2024-11-30 00:27 | 2024-11-30 00:28 | 25027844@mahindra.com | SACHIN PATIL | Machine Shop | Block line 1 | 2024-11-29 | 2 |  | Marposs | 28 | Zeroing error | [9 empty] | Closed |  | E |  | 30 | No
11 | 2024-12-03 02:22 | 2024-12-03 02:27 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-12-02 | 2 |  | Final Washing | 9 | machine stopped green with no error | all stations drained, LDR1 waiting to keep washed part on conveyor. | part not picked by LDL1. | part model not scanned at input conveyor |  |  | scanner trigger not taken | conveyor parts removed and released again. all sensors cleaned, scanner checked. |  |  | Closed |  | E and M | Basic Condition | 25 | No
12 | 2024-12-03 02:27 | 2024-12-03 02:30 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-12-02 | 2 |  | Marposs | 6 | D22 temperature probe advance timeout | probe cylinder not engaged forward | cylinder jammed |  |  |  | temp probe cylinder jammed | cylinder cleaned and little oil released in pneumatic pipe | temp probe cylinder replacement | umakant, ram | Open | 2024-12-15 | M | Deterioration | 15 | No
13 | 2024-12-03 16:30 | 2024-12-03 16:33 | 25025247@mahindra.com | RAMCHANDRA LATKE | Machine Shop | Block line 1 | 2024-12-03 | 1 |  | Final Washing | 105 | Airblower not working | Airblower not working | Blower motor MPCB trip | Motor winding Unbalance | Motor bearing Jam |  | Motor bearing Jam | Replaced motor |  | Umakant khairao | Closed |  |  | Weak Design |  | Yes
14 | 2024-12-04 02:33 | 2024-12-04 02:39 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-12-03 | 2 |  | Final Washing | 15 | Machine stopped in auto. no alarm. | part not picked by LDL1 | part not scanned | scanner not triggered |  |  | not identenfied yet. issue with scanner. found oil in scanner connectors. | scanner connectors cleaned and connected again with dielectric grease applied. no repeat after that. | scanner cleaning to be added in checksheets. | Umakant, Ram | Open | 2024-12-05 | E | Operating Condition | 30 | No
15 | 2024-12-04 07:12 | 2024-12-04 07:14 | 25027844@mahindra.com | SACHIN PATIL | Machine Shop | Block line 1 | 2024-12-03 | 3 | A | Final Washing | 5 | U jet shutter lock | [5 empty] | Proximity sensor dirty | Proximity sensor cleaned |  | Parag Gurav | Closed |  | E |  | 30 | No
16 | 2024-12-04 07:15 | 2024-12-04 07:17 | 25027844@mahindra.com | SACHIN PATIL | Machine Shop | Block line 1 | 2024-12-03 | 3 |  | Heller 815/ Heller 810 | 4 | Pallet clamping time out | [6 empty] | Hydraulic Oil level filled |  |  | Open |  | M |  | 20 | No
17 | 2024-12-04 07:18 | 2024-12-04 07:19 | 25027844@mahindra.com | SACHIN PATIL | Machine Shop | Block line 1 | 2024-12-02 | 3 |  | Heller 811 | 2 | Coolant unit priority faulty | [5 empty] | Conveyor chips accumulated | Chips cleaned |  |  | Closed |  | E and M |  | 10
18 | 2024-12-10 10:23 | 2024-12-10 10:27 | 25022622@mahindra.com | KUNAL ENDAIT | Machine Shop | Block line 1 | 2024-12-09 | 1 |  | Heller 815/ Heller 810 | 60 | spindle chiller fault and conditions | spindle mpcb trip | motor windings unbalanced |  |  |  | spindle motor & chiller panel interlocks. downtime exceeded | motor replaced |  | umakant, sandip, ram, parag | Closed |  | E and M | Weak Design | 155 | No
19 | 2024-12-14 07:36 | 2024-12-14 07:41 | 25025247@mahindra.com | RAMCHANDRA LATKE | Machine Shop | Block line 1 | 2024-12-14 | 3 | A | Heller 815/ Heller 810 | 28 | Work area clamping time exceed | Clamping time not reached as per switching point |  |  |  |  | Not found, pending fron OEM | Manually part unclamp and started | Action pending fron OEM | Umkantg | Open | 2024-12-31 | M | Weak Design | 28 | No
20 | 2024-12-15 00:15 | 2024-12-15 00:19 | 25027844@mahindra.com | SACHIN PATIL | Machine Shop | Block line 1 | 2024-12-15 | 2 |  | Heller 815/ Heller 810 | 70 | Pallet not clamp in work area | [5 empty] | Not found yet | Hydraulic oil level filled |  |  | Open | 2024-12-18 | E and M